	Product/Effort
	Results/Used For
	Future Plans/Next Steps

	DataONE Five Principles
	
	

	Data services Ecosystem 
· the idea of an effort to identify the administrative actors who support and influence research data services in academic and federal institutions)
	3 questions included in the Scientists/Educators follow up survey to be deployed this summer
	

	FAQs
	· 10 FAQs through 2 revisions by SCWG and 1 review by LT
· 3 of the high priority on ask.dataone.org
· Remaining ones need review
	

	WG Membership Participation Surveys
	· Prelim results Shared with external advisory board.
	

	Terms and Conditions	Comment by Miriam Davis: As of Joint UASC 2012:  “going to be reviewed and feedback provided, top of list for review, try to get out concurrent with or shortly after release.”
	· 
	

	Personas
	· 
	

	Usability tests of DataONE.org
	· Analysis done before both major releases of website 
· Eye tracking at ESIP/DUG Summer 2012, AHM 2012
· 
	

	Usability tests of ONEMercury
	· Feedback gathered at 2011 AHM
	

	
	· 
	

	DataONE Data Life Cycle
	· 
	

	Stakeholder Matrix
	· The stakeholder network allowed us to prioritize the communities in a manner that would facilitate the coordinated and successful growth of DataONE.	Comment by Miriam Davis: From SCWG Lightning Talk AHM 2012
· Foundational tool of DataONE - Helps guide the work of other working groups
· 	UA – communities to assess, testing tools
· 	Sustainability & Gov – strategic partners
· 	CI – identify users
· 
	

	Policies and Best Practices
	· 
	

	Scientists Baseline Assessment
	· Published
	

	Scientists Educators Follow Up Assessment
	· Drafted through several itterations.  Needs final review.  Planned to deploy summer 2013.
	

	Early Adopters (Figshare) Baseline Assessment
	· Deployed.  Collecting data.
	

	Academic Librarians Baseline
	· Published
	

	Academic Librians and Libraries
	· Review and resbumit
	

	Data Managers baseline
	· Article drafted for submission
	

	Academic Libraries
	· Published
	

	Metrics and Statistics
	· Reviewed metrics from PMP	Comment by Miriam Davis: From AHM 2012
· Reviewed what is being collected by infrastructure
· Discussed Statistical portal/ dashboard: Object Level Statistics (PMP), User Level Statistics (Persona), MN level Statistics, Macro level Statistics, Emerging interdisciplinary, DataONE.org statistics linkage (PMP)
·   	Comment by Miriam Davis: From Joint UASC WG 2012” Tier 1 member node: public data repository; public data only; no access controls; moderate availability level; uses Tier 1 API
Tier 2 member node: entry of authenticated user; log presence, use, responses of member node (including authentication), delivery of data
Tier 3 member node: authenticated user with write access to contribute datasets; public and restricted data
Tier 4 member node: responsbiility to back up their own and possibly other Tiers' data
CCIT WG will review”

Report of work, https://docs.dataone.org/member-area/working-groups/usability-and-assessment/meetings-usability-and-assessments-working-group/joint-u-a-sc-wg/metrics-and-statistics/notes%20on%20use%20metrics%2003May2012.ppt/view
Major Activities/Deliverables:
Metrics and stats presentation – combines work from last six months plus diagrams, https://docs.dataone.org/member-area/working-groups/usability-and-assessment/meetings-usability-and-assessments-working-group/joint-u-a-sc-wg/metrics-and-statistics/Metric%20-%20Stats%20pres_2.pptx/view
Diagrams, https://docs.dataone.org/member-area/working-groups/usability-and-assessment/meetings-usability-and-assessments-working-group/joint-u-a-sc-wg/metrics-and-statistics/mn-and-cn-relationship-diagrams

	

	Draft Data Citation White Paper
	· Used internally
	

	Draft of DataONE infrastructure for non-techies	Comment by Miriam Davis: From AHM 2011 report out:  Reviewed & Abstracted DAD 
Reviewed DUG MN docs & integrated relevant passages
Created framework for content (I interviewed some of you!)
2.5 page exec summary (overview, benefits, R&R, Costs, tech requirements)
8 page white paper with summarized architecture and pointers to original doc (references nearly all areas in original doc)
Written in language suitable for non-techie administrator
Draft still under construction but available at https://docs.dataone.org/member-area/working-groups/usability-and-assessment/ahm-oct-2011/Documentation%20v1.0.docx/view

	· 
	

	Communication audit and planning
	· 
	

	Environmental scan challenges and trends	Comment by Miriam Davis: SCWG Accomplishments in lightning talk AHM 2012
	· 
	

	Evaluation of Tools to Support Science activities	Comment by Miriam Davis: Completed.  Discussed at AHM 2011.
	· 
	



